## CMMI
Maturity Assessment | Level 1 | Level 2 | Level 3 | Level 4 | Level 5
Practice Area
Causal Analysis and Resolution (CAR)
Decision Analysis and Resolution (DAR)
Risk and Opportunity Management (RSK)
Organisational Training (OT)
Process Management (PCM)
Process Asset Development (PAD)
Peer Reviews (PR)
Verification and Validation (VV)
Technical Solutions (TS)
Product Integration (PI)
Managing Performance and Measurement (MPM)
Supplier Agreement Management (SAM)
Process Quality Assurance (PQA)
Configuration Management (CM)
Monitor and Control (MC)
Planning (PLAN)
Estimating (EST)
Requirements Development and Management (RDM)
Governance (GOV)
Implementation Infrastructure (II)
For an initial start on our performance and process improvement journey, the following practise areas could address critical problems:
Estimating (EST)
Planning (PLAN)
Monitor and Control (MC)
Technical Solutions (TS)
Product Integration (PI)
Requirements Development and Management (RDM)

## CM
Configuration Management
Summary
Planning for configuration management activities includes controlling work products developed or modified by the project. The work products placed under configuration management include: Baselines represent an approved version of a work product. They are intended to provide a clear and accurate understanding of the work product for future use. Add baselines to the configuration management system as they are developed. Systematically monitor and control changes to baselines and work products using: Configuration identification Configuration control Change management Configuration auditing functions of configuration management |  |  |  |  | Example of work products that can be placed under configuration management may include | Hardware and Equipment Drawing, diagrams and mockups; Tool configurations Product specifications Code and libraries Test tools and test scripts Requirements Compilers Architetcture documentation and design data
CONFIGURATION MANAGEMENT (CM)
INTENT
Manage the integrity of work products using configuration identification, version control, change control, and audits.
VALUE
Reduces loss of work and increases the ability to deliver the correct version of the solution to the customer.
LEVEL | VALUE | CMMI Practises | People | Technology
LEVEL 1
CM 1.1
Perform version control. | Increases customer satisfaction by ensuring that the correct solutions is delivered | List the work products to be placed under version control and keep it updated.
LEVEL 2
CM 2.1 |  |  |  |  | Example:
Identify items to be placed under configuration management. | Reduces risk of rework and ensures that the right version is delivered to the customer. | Assign unique identifiers to configuration items. |  |  | Identified confirguation items | Charateristics may include: Owner or author Type of work product or solution Key feautures Purpose of Item Version Security
Describe the important characteristics for each configuration item.
Specify when each item is placed under configuration management.
CM 2.2
Develop, keep updated, and use a configuration and change management system. | Reduces the cost and effort needed to control the integrity of work products and solutions. | Describe how the items and changes to them are controlled, used, and managed throughout the solution lifecycle. |  |  | A Configuration management system: | Enables consistent and controlled access to work products and solutions and provides the ability to restore a previous version, configuration, or baseline. May include both manual or automated methods, tools or complete systems to control work products; May be embedded or integrated with other tools to produce work products and solutions; Includes tge procedures for accessing the system
|  | Establish methods to manage multiple levels of control. |  |  |  | The level of control is typically selected based on work objectives, risk, type and resources. Example of levels of ontrol include: - Uncontrolled: Anyone can make changes - Version controlled" Authors or owners control changes - Baselined: A designated authority authorised and controls changes, and notifies affected stakeholders
Provide access control to ensure authorized access to the configuration management system.
|  | Store and retrieve configuration items in the configuration management system. |  |  |  | Check-in and check-out functions
Preserve the contents of the configuration management system.
Update the configuration management system as necessary.
CM 2.3
Develop or release baselines for internal use or for delivery to the customer. | Ensures the integrity of the work products. | Obtain authorization or approval before developing or releasing baselines of configuration items. |  |  |  | Represent a baseline by assigning an identifier to a configuration item or a collection of configuration items and associated entitties at a point in time. As solution evolves, multi0ple baselines can exist.
|  | Develop or release baselines only from configuration items in the configuration management system. |  |  |  | A software baseline can include: - a unique identifier - version release notes - a set of requirements - design - interfaces - source code files - test cases, etc - build files - user documentation, such as installation, operational | A hardware baseline can include: - a unique identifier - version release notes - design - interfaces - drawings or schematics - Test environment
Record the set of configuration items contained in a baseline.
|  | Make the current set of baselines available. |  |  |  | Only stakeholders with approved access should be able to access the baseline information. Aditionally, other techniques such as "build cop", "don’t break the build", "release on demand", "continuous integration:, and "continuos delivery" to manage baselines
CM 2.4
Manage changes to the items under configuration management. | Reduces costs and schedule impacts by ensuring that only authorized changes are made. | Initiate and record change requests. Typically includes: Changes to requirements Failures and defects in work products Needs from stakeholders, end users, and customers Description of the impact to work products and solutions |  |  |  | Typically includes: - Changes to requirements - failures and defetcs in work products need from stakeholders, end users and custoemrs - Descriptin of the impat to work products and solutions
Analyze the impact of change requests. Analysis should consider impacts to: Technical and project requirements Impact beyond the immediate project or contract requirements Impact on release plans Cost Schedule Quality Functionality Commitments
Categorize and prioritize change requests. Typically includes: Allowing for emergency changes Allocating changes to future baselines
Review and get agreement on change requests to be addressed in the next baseline with affected stakeholders.
Track the status of change requests to closure.
Incorporate changes in a manner that maintains integrity. Examples of check-in and check-out include: Confirming the revisions are authorized Updating the configuration items Maintaining versions of work products Archiving the replaced baseline and retrieving the new baseline Commenting on the changes made Assigning changes to related work products
CM 2.5
Develop, keep updated, and use records describing items under configuration management. | Accurate descriptions of the configuration items and status of changes enables reduction of rework. | Record configuration management actions in sufficient detail so the content and status of each configuration item is known and previous versions can be recovered.
Ensure that affected stakeholders have access to and knowledge of the configuration status of configuration items.
Specify the differences among previous, related, and latest versions of baselines.
CM 2.6
Perform configuration audits to maintain the integrity of configuration baselines, changes, and content of the configuration management system. | Increases customer satisfaction and stakeholder acceptance by ensuring that the customer receives the agreed-on and correct versions of work products and solutions. | Assess the integrity of baselines and generate action items to address identified issues. Examples include: Physical work product reviews verifying changes Functional work product reviews verifying changes Comparison of approved changes versus actual changes made in a work product |  |  |  | Configuration audits and review results, and with this there should be objectives for and outcomes of audits in enough detail to take action;
Confirm integrity of configuration management records.
Review the structure and integrity of items in the configuration management system.
Record action items and track them to closure.

## EST
Estimating
SUMMARY
Estimation provides the basis for making commitments. An estimate takes into consideration the scope, size, and complexity of the work. Base the estimate on the available information. Record any uncertainty as a risk. Uncertainty or risk in a commitment can be handled by: Providing an initial commitment with an understanding that the initial commitment may be changed if the scope changes Defining milestones to refine an initial commitment range to produce a final commitment after more investigation Committing to the known parts of the project, and committing to the remainder of the work after further investigation and definition Historical data describing the relationship between measured size and resources such as effort, cost, and schedule should be used when planning future work. A good understanding of historical data is critical to successful estimating. Use historical data when planning future work and to calibrate estimation formulas and models. Record qualitative information such as context, methods, tools and techniques used, and lessons learned from past projects. Estimate and track several aspects of the work to realize value. For example, based on the table below, how complete is the work?
ESTIMATING (EST)
INTENT
Estimate the size, effort, duration, and cost of the work and resources needed to develop, acquire, or deliver the solution.
VALUE
Estimation provides a basis for making commitments, planning, and reducing uncertainty, which allows for early corrective actions and increases the likelihood of meeting objectives.
MATURITY ASSESMENT
LEVEL | VALUE | CMMI Practises | People | Technology
LEVEL 1
EST 1.1
Develop high-level estimates to perform the work. | A high-level estimate addresses work size, cost, and schedule incertainties to avoid pursuing work that may result inschedule or budget overruns. | A High-level estimate is typically: - a rough draft, top-down estimate (also called a rough order of magnitude estimate) - Based on identified or recorded assumptions and uncertaiinty - Developed quickly - Based on previous knowlegde and experience
LEVEL 2
EST 2.1
Develop, keep updated, and use the scope of what is being estimated. | Ensure the entire solution is addressed which increases the likehood of meeting objectives and avoiding rework. | The scope: - Includes the work effort - Defines the solution to be developed, delivered, or acquired - Results in the information needed to estaimate the size, effort, cost and duration - Addresses any resources that must be acquired or will be consumed during the project |  |  | - Lists of tasks ans activities or Work Breakdown Structure (WBS) - List of needd resourced - Work flow diagram
EST 2.2
Develop and keep updated estimates for the size of the solution. | Well-defined estimates allow work tracking and timely corrective actions to deliver the solution on time and within budget | Size is the primary inut to many estimation models. Estimation is not a one-time activifity that is only performed before or at the start of the project. It is a recurring activity where the estimate is adjusted as new information becomes availble throughout eh lifecycle of a solution, operations and maintenance, or for services produced and delivered |  |  | Methods for determining size include: Analogy Delphi 3-point estimation Parametric estimation The project estimation methods and their use may change over time as the understanding of the relationshop of solutions charactericts to size improves
EST 2.3
Based on size estimates, develop and record effort, duration, and cost estimates and their rationale for the solution. | Enables a better basis for commitments and imporves accuracy of the estimates, leading to better decission making; | Collect and use historical data to develop, calibrate or recaibrate mdels or methods to tranaform size and complexity into effort, duraction, and cost estimates; |  |  | refer to age 118 for more detail
LEVEL 3
EST 3.1
Develop and keep updated a recorded estimation method. | Maximises consistency and efficciency for developeing accurate estimates and icnreases the likelohood of meeting objectives | Refer to page 122 for estimation methods
EST 3.2
Use the organizational measurement repository and process assets for estimating work. | Increases estimation preciciosn, accuracy and consistency enabling better decciosn makig, a higher likelohood of meeting objectives and reduced risk; | Using organisational assets as a basis for estimating leverages the data nd experinece from previous porjects to improve the relaibility of estimates for similir work. Select the most appropriate estimation method and use it to produce the estimates. When using org assets consider: - Typ of work; Tailoring performed Rationale used to select the historical data - historical and validated data from this work or similiar work and its context

## MC
Monitor and Control
SUMMARY
The term "project plan" refers to the overall plan for managing the project and includes a coherent description of who does what and when for creating, updating, or delivering a solution. The project plan can be a stand-alone document or distributed across multiple documents, and provides a way to track and communicate actual progress and determine if corrections are needed. Tracking progress typically consists of comparing actual values to planned or estimated values for: Size Complexity Effort Cost Schedule Quality Milestones Knowledge and skills Resources Stakeholder involvement Commitments Transition to operations and support Tracking actuals against estimates supports managing the expectations of customers and stakeholders. Take corrective actions when actual values deviate significantly from expected values. These corrective actions may include: Revising the strategy for accomplishing the work Updating objectives Revising the plan Revising the estimates Establishing or modifying agreements and commitments Updating risk management activities and work products If corrective actions are required to resolve significant deviations from project plans, define and track these actions to closure.
MONITOR AND CONTROL (MC)
INTENT
Provide an understanding of the project progress so appropriate corrective actions can be taken when performance deviates significantly from plans.
VALUE
Increases the probability of meeting objectives by taking early actions to adjust for significant performance deviations.
MATURITY ASSESMENT
LEVEL | VALUE | CMMI Practises | People | Technology
LEVEL 1
MC 1.1
Record task completions. | Knowing how much work remains enables the team and senior management to make better decissions to acheiev objectives | Record task completion - although tasks can be given a percentage completion, this may lead ti inaccurte status reporoting such as 90% done 90% of the time. One way to avoid this is to only show 100% complete on not complete
MC 1.2
Identify and resolve issues. | Resolving issues helps prevent uncontrolled cost and schedule creep | Record the issue in the issue and action item list; Assign responsibility for resolving the issue or action item; Assign a due date; Track issues and actoipsn items to closure
LEVEL 2
MC 2.1
Track actual results against estimates for size, effort, schedule, resources, knowledge and skills, and budget. | Identififes significant deviations so more effective corrective actionas can be taken which increases the likehood of meeting objectives | - Track actual results to plans and estimates; - Monitor resources provided and used; - Monitor the knowlegde and skills of workgroup members; Monitor commitments against those identified in the project plan; - Record significant differences in planned vs actual values; - Record of significant deviations |  |  | Record associated contextual information when tracking actual results versus estimates to help understand what the measuremnt data represents.
MC 2.2
Track the involvement of identified stakeholders and commitments. | Managing stakeholder involvement is critical to successful work completion | - Periodically review and record the status of stakeholder involvement - develop recommendations and coordinate actions to resolve issues
MC 2.3
Monitor the transition to operations and support. | Solutions are smoothly transiaiotns and successfully implemented ensuring expected benefits are obtained; | - Monitor the capabilities of operations and support to receive, store, use and maintain new or midified solutions - Monitor training delivery to stakeholders involved in recieeivng, storing, using and maintaining solutions; - review and analyse the results of transition activvities;
MC 2.4
Take corrective actions when actual results differ significantly from planned results and manage to closure. | Managing corrective actiosn can increase the probabaility that objectives wil be met | - Collect issues for analysis, examples: Issues discovered when performing technical reviews, verification and validation - Significant deviations in project planning parametrs - Significant changes in risk status - Anayse issues to decide if corrective action is needed - take corrective action on identified issues |  |  | Collect and analyse issues and decide on corrective actions to address them. Manage the corrective actions to closure. Actions can be autoimated, performed manually, or a combination of the two. Example may include: - rebalancing worklaod among resources - improving proceses to allow for greater productivity, efficiency and effectiveness - tuning to optimise and improve capacity or performance
LEVEL 3
MC 3.1
Manage the project using the project plan and the project process. | Helps to ensure necessary activities are performed which reduces rework and improves the likehood of achieving objectives | - Manage the project activities using process process and related plans - Collect and analyse selected measurements to manage the project and support the organisation needs - Periodically review and align project performance with organisational, customer and end requirements and objectives
MC 3.2
Manage critical dependencies and activities. | Managing critical dependencies can significanlty reduce risk and increase the likelihood of meeting objetcives | - Updated critical dependacnies; - Record agendas and meeting minutes - Recorded issues like supplier delays, stakehodler involvement and recommendations for resolving of issues
MC 3.3
Monitor the work environment to identify issues. | An effective, safe, and healthy work environment helps ensure objectives are met | Work environment elements may inlcude: - standard workstation hardware and software - standard production and calibration equipment - management and leadership Remove or reduce interruptions or distractions that degrade performance
MC 3.4
Manage and resolve issues with affected stakeholders. | Resolving issues early increases the likehood of meeting objectives |  |  |  | The purpose of this practise is to identify, communicate, and resolve issues with affected stakeholders. When notified and engaged early in the process, stakehodlers can more effectivley address their responsibilities to ensure they stay in sync with objectives and plans. Examples of issues include: - incolplete requirements - design defects - late critical dependencies and comitments - solution problems - unavailable critical resources

## RDM
REQUIREMENTS DEVELOPMENT AND MANAGEMENT (RDM)
Summary
This practice area describes three types of requirements: 1. Customer or business requirements 2. Solution requirements 3. Interface or connection requirements Taken together, these requirements address the needs of stakeholders, including needs pertinent to various lifecycle phases and attributes (e.g., responsiveness, security, quality). Requirements can also include constraints. All projects have requirements. Requirements are the basis for developing the right solutions. Developing requirements includes: Eliciting, analyzing, validating, and communicating customer needs, expectations, and constraints Prioritizing customer requirements to understand what will satisfy stakeholders given resource constraints Developing the lifecycle requirements of the solution Developing operational concepts and scenarios Developing the customer functional and quality attribute requirements, including descriptions, decompositions, and allocating requirements to functions Developing initial solution requirements consistent with customer requirements Customer requirements are further refined into solution and interface or connection requirements. In addition to customer requirements, solution and interface or connection requirements are derived from the selected design solutions. Identify and refine requirements throughout the project. Analyze design decisions, subsequent corrective actions, and feedback for impact on requirements. Analyses can be used to understand, define, and select the requirements.
In addition, the definition may specify design constraints. Some quality attributes will emerge as architecturally significant and drive the development of the solution architecture. Quality attributes may address: Solution availability Ability to sustain and maintain Timeliness, throughput, and responsiveness Consistency Security Scalability Analyses are iterated until there is enough detail to develop the solution or a portion of the solution. Analysis of requirements and the operational concepts and scenarios may result in identifying more requirements, including: Constraints of various types Technological limitations Costs Time constraints Risks Functionality, support, and maintenance concerns Issues implied but not explicitly stated by the customer
INTENT
Elicit requirements, ensure common understanding by stakeholders, and align requirements, plans, and work products.
VALUE
Ensures that customer's needs and expectations are satisfied.
MATURITY ASSESSMENT
LEVEL | VALUE | Agile Ceromonies / Practises | People | Technology
LEVEL 1
RDM 1.1 |  | CMMI Practises
Record requirements. | Recorded requirements are the basis for successfully addressing customer needs and expectations. | Examples include: List of requirements Statement of work Use cases
LEVEL 2
RDM 2.1
Elicit stakeholder needs, expectations, constraints, and interfaces or connections. | Active elicitation of requirements ensures a deeper mutual understanding of the requirements and increases the likelihood that the customer will be satisfied. | Techniques to elicit needs include: Technology demonstrations Interim project reviews Questionnaires Interviews Scenarios (operational, sustainment, and development) Walkthroughs Quality attribute elicitation workshops with stakeholders Prototypes and models Brainstorming Quality function deployment Market surveys Beta testing Extraction from sources such as documents, standards, or specifications Observation of existing solutions, environments, and workflow patterns Use cases Business case analysis Reverse engineering (for legacy solutions) Customer satisfaction surveys Viewpoint analysis
RDM 2.2
Transform stakeholder needs, expectations, constraints, and interfaces or connections into prioritized customer requirements. | Ensure customer priorities are addressed to minimize the cost of rework during acceptance, and maximize customer satisfaction. | Technical requirements, such as: External interface or connection Internal interface or connection (developed during design) Functional Quality Operational Performance Verification Validation Acceptance criteria Safety Security Nontechnical requirements, including: Price and cost Delivery constraints Resource constraints Training Customer interactions (e.g., status reporting, meetings)
RDM 2.3
Develop an understanding with the requirements providers on the meaning of the requirements. | Helps to ensure the correct solution is delivered which increases customer satisfaction. | Defintion of Done (Agile)
RDM 2.4
Obtain commitment from project participants that they can implement the requirements. | Ensures commitments are well understood to minimize delays and rework. | Negotiate commitments before work starts (Backlog Grooming)
RDM 2.5
Develop, record, and maintain bidirectional traceability among requirements and activities or work products. | Ensures consistency between requirements and the solution which increases the likelihood of customer satisfaction. | Records of bidirectional requirements traceability
RDM 2.6
Ensure that plans and activities or work products remain consistent with requirements. | Minimizes rework by eliminating inconsistencies between requirements and related artifacts. | Maintaining bidirectional traceability is critical to maintaining consistency between requirements, work products, and plans.
LEVEL 3
RDM 3.1
Develop and keep requirements updated for the solution and its components. | Ensures the built solutions meet the customers' needs and expectations in a consistent way across the organization. | Stories, technical stories, architectural stories
RDM 3.2
Develop operational concepts and scenarios. | Enables customers to understand, confirm, and commit to how their requirements will be met. | Identify and develop scenarios, consistent with the level of detail in the stakeholder needs, expectations, and constraints. Ensure scenarios address quality attribute, functions, or other factors. Iteratively refine operational concept and scenarios to include more detail as decisions are made and as lower level requirements are developed; for example, describe interactions among the: Solution End users Environment Boundaries and constraints
RDM 3.3
Allocate the requirements to be implemented. | Increases customer satisfaction by delivering a complete solution that meets requirements. | Requirements are typically allocated to: Logical design - As the operational concept evolves, allocate requirements to logical entities (e.g., functions, processes) that help relate the requirements to the operational concept. These logical entities serve to organize the requirements and assist in the synthesis of the technical solution. Physical design - As the technical solution is selected or developed, allocate requirements to solution components. Components Interfaces or connections Delivery increments
RDM 3.4
Identify, develop, and keep updated interface or connection requirements. | Reduces rework and risk due to incompatible internal and external interfaces or connections. | As the design progresses, the architecture will be altered by technical solution processes, developing new interfaces or connections between internal components and components external to the solution. Management of the interfaces or connections may include: Maintaining consistency of the interface or connection Complying with architectural decisions and constraints Resolving conflict, non-compliances, and change issues
RDM 3.5
Ensure that requirements are necessary and sufficient. | Avoids rework by only delivering necessary solutions. | Analyze requirements to ensure they are: Relevant Complete Feasible Maintainable Not in conflict Analyze operational concepts and scenarios to refine customer needs, constraints, and interfaces or connections, and to discover new requirements. This analysis can result in more detailed operational concepts and scenarios and supports deriving new requirements.
RDM 3.6
Balance stakeholder needs and constraints. | Increases stakeholder satisfaction while addressing conflicting requirements and constraints. | Analysis includes use of: Models Simulations Prototypes A risk assessment on the requirements and definition of required functionality, performance, and quality attributes Assessment of the requirements on cost, schedule, functionality, and quality
RDM 3.7
Validate requirements to ensure the resulting solution will perform as intended in the target environment. | Avoids rework cost and increases satisfaction by delivering a solution that meets customer expectations and needs. | Sprint Demo

## PLAN
Planning
SUMMARY
Planning includes developing budgets and schedules based on estimates; identifying the appropriate set of stakeholders and tasks; managing risks; determining the necessary resources; and developing and keeping the project plan updated to reflect how work is being performed.
PLANNING (PLAN)
INTENT
Develop plans to describe what is needed to accomplish the work within the standards and constraints of the organization, including the: Budget Schedule Resource demand and capacity Quality Functionality requirements Risks and opportunities Plans also describe: The work to be performed Applicable organizational set of standard processes, assets, and tailoring guidelines Dependencies Who performs the work Relationships with other plans Stakeholders and their role
VALUE
Maximizes business return on investment by focusing management and improvement efforts on cost, schedule, and quality performance.
MATURITY ASSESMENT
LEVEL | VALUE | CMMI Practises | People | Technology
LEVEL 1
PLAN 1.1
Develop a list of tasks. | Ensure that the work needed to meet customer requirements is identified to increase customer satisfaction. | Task list Includes: - Tasks to be performed and their timeline - Descritpion of activivites to assist in + Assigning team memebers + Understanding what is expected
PLAN 1.2
Assign people to tasks. | Ensure that tasks will be performed to meet requirements and satisfy the customer | - Assign an individual who is responsible for each task - Assign any additional people to the task - Review assignments with the assigned individuals - Record assignemnts in task list
LEVEL 2
PLAN 2.1
Develop and keep updated the approach for accomplishing the work. | Maximise project success by keeping the affected stakleholders focused on accomplishing their specific objectives | - Identify the objectives of the project - Idenitfy the approach to be used to achieve objcectives - Identify requiremets - Record business considerations -Define and record rhe project lifecycle Identiyf major resource needs and constraints - etc
PLAN 2.2
Plan for the knowledge and skills needed to perform the work. | Enable efficicent and effective use of persoinnel resources | - Identify the knowledge and skills needed to perform the work - Determine the gaps between the knowledge and skills needed versus those held by the currenbtly assigned people - Select methods for providing needed knowledge and skills - Incorporate selected methods into the project plan - Inventory of skill needs
PLAN 2.3
Based on recorded estimates, develop and keep the budget and schedule updated. | Early detection of significant deviations from the budget and schedule enables timely management and corrective actions needed to achieve obtjectves | - Identify major milestones - Identify schedule assumptions - Identify constraints - Identify task dependancies - Identify resources - Idenityft and analyse risks - Based on estimates, develop the budget and schedule, and keep them updated - Estabslih corrective action criteria
PLAN 2.4
Plan the involvement of identified stakeholders. | Ensure that staekolders needs are addressed when they arise, reducing the amount and cost of rework | - Develop a list of stakeholders - Identify the involvement of each stakeholder - Rexoird when the involvement is required |  |  | Example mechanisms for involving stakeholders of service systems transitions inlcude: - Automatic notifications from the servic system - Posted information within the service system - Progress reviews, discussion or approaches - Communications through newsletters - Updates of user guides and user procedures - Updates of user training
PLAN 2.5
Plan transition to operations and support. | Minimises surprises and rework during adoption and deployment | - Determine transition scope and objectives - Determine transistion requirements and criteria - Determine approach to transition - Develop schedule dfor transition - Determine transition responsibilities and resources including post-transition support
PLAN 2.6
Ensure plans are feasible by reconciling available and estimated resources. | Increases likelihood that the objectives will be acheved by ensuring that needed resources are available and committed to throughout the proeject | - Perform resource leveling to adjust scheduling of tasks and resources - Ensure comittments are supported by adequate personnel or other required resources - Negotiate commitments with affected stakeholders |  |  | Overcomitted resources can be reconcviled by: - Resource leveling the schedule - Modifying or deferring requiremenets - Negotiating more rsources - Finding ways to increase productivity
PLAN 2.7
Develop the project plan, ensure consistency among its elements, and keep it updated. | A consistent project plan helps to ensure efficicent and effective communication and achievement of objectives | - ecord thr project plan - Review the project plan with affected stakeholders - Revise the project plan as necessary
PLAN 2.8
Review plans and obtain commitments from affected stakeholders. | Rework is reduced and the likilyhood of achieving onbhectives is increased through a consistent understanding and commitment to the plan | - Ensure individuals are involved in reviewing the work they are responsible for and the inputs that initiate the work - Record commitments - Review and approve project commitments |  |  | Example of plans that have been used by large organisations inlcude: - Integrated Master Plan - an even driven plan that records significant accomplishments with pass/fail crieteria for both business and technical elements - Integrated Master Schedule - an intergated and network multi-laywered schedule of project tasks required to complete the work recorded - System Engineering Management Plan - a plan that details the integrated technical effort accros the project - Systems Engineering Master Schedule - an event-based schedule that contains a compliation of key technical accomplishments, each with measureable crietaerira, requiring successful completion toi pass identifgied events - Sustems engineering Detailed Schedule - a detailed, time dependant, task-orientted sxchedule that associated dates and milestones
LEVEL 3
PLAN 3.1
Use the organization's set of standard processes and tailoring guidelines to develop, keep updated, and follow the project process.
PLAN 3.2
Develop a plan and keep it updated, using the project process, the organization's process assets, and the measurement repository.
PLAN 3.3
Identify and negotiate critical dependencies.
PLAN 3.4
Plan for the project environment and keep it updated based on the organization's standards.
LEVEL 4
PLAN 4.1
Use statistical and other quantitative techniques to develop and keep the project processes updated to enable achievement of the quality and process performance objectives.

## MPM
Manage Performance and Measurement
SUMMARY
This practice area helps to: Ensure that benefits and business performance are the leading factors in driving performance and improvement. Change the paradigm from "process improvement leads to performance improvement" to "performance is the primary driver of process improvement". Use the results of measurement and analysis to manage and control performance at various work and business levels. Performance and measurement management includes: Setting objectives for: The business Measurement and performance Quality and process performance Allocating and tracing objectives to subordinate levels in the business and processes Defining measurements to improve the understanding of progress towards achieving the objectives Analyzing measurement and performance data to: Understand the relationship and interactions between performance and process Define and take actions to address any observed issues with achieving objectives Make the performance results and related benefits clearly visible to all stakeholders The term “measurement and performance objectives” is used to describe quantitative or qualitative objectives that do not require the additional rigor of statistical and other quantitative techniques. In this practice area, the term "quality and process performance objectives" is used within high maturity practices. These objectives include the use of statistical and quantitative analysis on the related data.
MANAGING PERFORMANCE AND MEASUREMENT (MPM)
INTENT
Manage performance using measurement and analysis to achieve business objectives.
VALUE
Maximizes business return on investment by focusing management and improvement efforts on cost, schedule, and quality performance.
MATURITY ASSESMENT |  | CMMI Practises
LEVEL | VALUE | Agile Ceromonies / Practises | People | Technology
LEVEL 1
MPM 1.1
Collect measures and record performance.
MPM 1.2
Identify and address performance issues.
LEVEL 2
MPM 2.1
Derive and record measurement and performance objectives from selected business needs and objectives and keep them updated.
MPM 2.2
Develop, keep updated, and use operational definitions for measures.
MPM 2.3
Obtain specified measurement data according to the operational definitions.
MPM 2.4
Analyze performance and measurement data according to the operational definitions.
MPM 2.5
Store measurement data, measurement specifications, and analysis results according to the operational definitions.
MPM 2.6
Take actions to address identified issues with meeting measurement and performance objectives.
LEVEL 3
MPM 3.1
Develop, keep updated, and use organizational measurement and performance objectives traceable to business objectives.
MPM 3.2
Follow organizational processes and standards to develop and use operational definitions for measures and keep them updated.
MPM 3.3
Develop, keep updated, and follow a data quality process.
MPM 3.4
Develop, keep updated, and use the organization's measurement repository.
MPM 3.5
Analyze organizational performance using measurement and performance data to determine performance improvement needs.
MPM 3.6
Periodically communicate performance results to the organization.
LEVEL 4
MPM 4.1
Use statistical and other quantitative techniques to develop, keep updated, and communicate quality and process performance objectives that are traceable to business objectives.
MPM 4.2
Select measures and analytic techniques to quantitatively manage performance to achieve quality and process performance objectives.
MPM 4.3
Use statistical and other quantitative techniques to develop and analyze process performance baselines and keep them updated.
MPM 4.4
Use statistical and other quantitative techniques to develop and analyze process performance models and keep them updated.
MPM 4.5
Use statistical and other quantitative techniques to determine or predict achievement of quality and process performance objectives.

## PI (CI - CB)
Continuous Build / Integration
Summary
Continuous build/continuous integration is an approach to continuous testing and product integration popular with agile teams that was first introduced in Extreme Programming (XP). CB/CI can be used in any type of software engineering environment and is not limited to agile teams. In a CB/CI environment, an application is built, and unit and (in some cases integration) tested, using automated tools each time new code is “checked-in” to the code management system. It was originally introduced as a companion to “test-driven development (TDD),” a technique in which test cases are written concurrently with user stories.
The practice of CB/CI requires a code repository (a major component of any configuration management system) as well as servers and scripts that automatically (and at frequent intervals) collect newly checked-in code, build and compile the system, run automated unit and integration tests, and publish the results. An extension of CB/CI is to automatically deploy the built system to a test or sometimes even a production environment (this extension is not common). CB/CI can benefit from these practices contained in Verification, Technical Solution, Product Integration, and Configuration Management.
PRODUCT INTEGRATION (PI)
INTENT | VALUE
Integrate and deliver the solution that addresses functionality and quality requirements. | Increases customers' satisfaction by giving them a solution that meets or exceeds their functionality and quality requirements.
MATURITY ASSESSMENT
LEVEL | VALUE | Agile Ceromonies / Practises | COBIT 5 Practise | COBIT 5 Description | People | Technology
LEVEL 1
PI 1.1
Assemble solutions and deliver to the customer. |  | CMMI Practises
LEVEL 2
PI 2.1
Develop, keep updated, and follow an integration strategy.
PI 2.2
Develop, keep updated, and use the integration environment.
PI 2.3
Develop, keep updated, and follow procedures and criteria for integrating solutions and components.
PI 2.4
Confirm, prior to integration, that each component has been properly identified and operates according to its requirements and design.
PI 2.5
Evaluate integrated components to ensure conformance to the solution's requirements and design.
PI 2.6
Integrate solutions and components according to the integration strategy.
LEVEL 3
PI 3.1
Review and keep updated interface or connection descriptions for coverage, completeness, and consistency throughout the solution's life.
PI 3.2
Confirm, prior to integration, that component interfaces or connections comply with interface or connection descriptions.
PI 3.3
Evaluate integrated components for interface or connection compatibility.
VERIFICATION (VER)/VALIDATION (VAL)
INTENT | VALUE
Processes for this Practice Area will: Verify that selected solutions and components meet their requirements Validate that selected solutions and components fulfill their intended use in their target environment | Verification and validation of selected solutions and components throughout the project increases the likelihood that the solution will satisfy the customer.
MATURITY ASSESSMENT
LEVEL | VALUE | EXAMPLES
LEVEL 1
VV 1.1
Perform verification to ensure the requirements are implemented and record and communicate results.
VV 1.2
Perform validation to ensure the solution will function as intended in its target environment and record and communicate results.
LEVEL 2
VV 2.1
Select components and methods for verification and validation.
VV 2.2
Develop, keep updated, and use the environment needed to support verification and validation.
VV 2.3
Develop, keep updated, and follow procedures for verification and validation.
LEVEL 3
VV 3.1
Develop, keep updated, and use criteria for verification and validation.
VV 3.2
Analyze and communicate verification and validation results.

## TS
Technical Solutions
SUMMARY
The Technical Solution practices can be applied: To products or product components To services, service systems, and service components At any level of the product or service architecture When implementing Technical Solution practices, focus on meeting functional and quality requirements. Design and build solutions that meet customer requirements by: Developing, evaluating, and selecting cost-effective design solutions. These selected design solutions can be called "design approaches", "design concepts", or "preliminary designs." Developing designs detailed enough to support implementation of the selected design solutions. Implementing the designs as a product, service, or component.
TECHNICAL SOLUTIONS (TS)
INTENT
Design and build solutions that meet customer requirements.
VALUE
Provides a cost-effective design and solution that meets customer requirements and reduces rework.
MATURITY ASSESSMENT
LEVEL | VALUE | CMMI Practises | People | Technology
LEVEL 1
TS 1.1
Build solution to meet requirements.
LEVEL 2
TS 2.1
Design and build a solution to meet requirements.
TS 2.2
Evaluate the design and address identified issues.
TS 2.3
Provide guidance on use of the solution.
LEVEL 3
TS 3.1
Develop criteria for design decisions.
TS 3.2
Develop alternative solutions for selected components.
TS 3.3
Perform a build, buy, or reuse analysis.
TS 3.4
Select solutions based on design criteria.
TS 3.5
Develop, keep updated, and use information needed to implement the design.
TS 3.6
Design solution interfaces or connections using established criteria.

## ValueStream Analysis
ValueStream Analysis

## Categories and Capabilities
Categories | Capability | Practise Area
Doing | Ensuring Quality | Requirements Development and Management (RDM)
Process Quality Assurance (PQA)
Verification and Validation (VV)
Peer Reviews (PR)
| Engineering and Developing Products | Technical Solutions (TS)
Product Integration (PI)
| Delivering and Managing Services | Service Delivery (OUT OF SCOPE)
Service System Transition (OUT OF SCOPE)
| Selecting and Managing Suppliers | Solicitation and Supplier Selection (OUT OF SCOPE)
Supplier Agreement Management
Managing | Planning and Managing Work | Monitor and Control (MC)
Planning (PLAN)
Estimating (EST)
Capacity and Availability Management
| Managing Business Reslience | Risk and Opportuntity Management (RSK)
Incident Resolution and Prevention (OUT OF SCOPE)
Continiuity (OUT OF SCOPE)
| Managing the Workforce | (SO OUT OF SCOPE)
Enabling | Suporting Implementation | Causal Analysis and Resolution (CAR)
Decision Analysis and Resolution (DAR)
Configuration Management (CM)
| Managing Safety | OUT OF SCOPE
| Managing Security | OUT OF SCOPE
Improving | Improving Performance | Process Management (PCM)
Process Asset Development (PAD)
Managing Performance and Measurement (MPM)
| Building and Sustaining Capability | Governance (GOV)
Implementation Infrastructure (II)